## Form W1
CONTRACT NO: PWD/HO/B130/2019
PERFORMANCE-BASED CONTRACT FOR THE LONG-TERM MANAGEMENT AND MAINTENANCE OF STATE ROADS [JALANRAYA NEGERI (JRN)] IN SARAWAK - PACKAGE 4 (MIRI DIVISION)
REQUEST FOR INSTRUCTED WORK (FORM W1)
| Service Provider's Proposal Ref: |  | EC/JKR/IW/2021/22 |  |  |  | Division : | MIRI
| Date : |  | 18.06.2020 |  |  |  | RMU : | MIRI
WITH REFERENCE TO THE ABOVE, WE SEEK YOUR CONSIDERATION TO CARRY OUT THE WORK AS DESCRIBED BELOW AS INSTRUCTED WORK (IW) AND AT THE ESTIMATED COST SHOWN:
PART A: NAME OF SITE/LOCATION
| Road Code: | Q3187 |  |  |  | Chainage Location: |  | CH28+970
| Road Name: | JALAN MIRI MARUDI | [5 empty] | Approved IW Ref. (to be given by S.O.):
PART B: DETAILS OF WORKS
(Refer to attachment, if any)
Slope failure at KM28+970 affected about 20m of the road length.
Proposed slope rehabilitation were consist of slope and minor pavement repair. Slope
repair considers stabilize slope, includes turfing, construction of RC and resurfacing
work on the pavement.
| Proposed Design Duration: |  | 3.1 | months |  | Proposed Completion of IW Period: |  |  |  | 6.5 | months
PART C: COST ESTIMATE (refer to attached Bill of Quantities, Drawings and all its associated supporting documents )
| Physical Works | [7 empty] | 687018.55
| General and Preliminaries | [7 empty] | 34350.93
| Consultancy Fees + Government Tax @ % (If any) | [7 empty] | 0
| Survey Works + Government Tax @ % (If any) | [7 empty] | 0
| Site Investigation + Government Tax @ % (If any) | [7 empty] | 0
| Any other cost: | [7 empty] | 0
| Estimated Total Cost | [7 empty] | 721369.48
| Stamp and Signature: | Requested by Service Provider's Representative or Site Agent: |  |  | Verified by S.O. or his representative: |  |  | The reinstatement work required is considered as CRITICAL / URGENT. I hereby recommend that the work to be carried out as Instructed Works.
| Name: | Mohd. Riduan Osman |  |  | Chong Chi Fam
| Designation: | Regional Manager |  |  | Jurutera Bahagian, J52(LS)
| of: | Endaya Construction Sdn. Bhd. |  |  | JKR Bahagian Miri
| Date: | 01.09.2021 |  |  | 02.09.2021
Name for this Instructed Work Proposal: (to be given by S.O. / S.O.'s Rep.)
PROPOSED REHABILATION FOR SLOPE AT CH28+970, Q3178 JALAN MIRI MARUDI
ENDAYA CONSTRUCTION SDN BHD (049693-V)

## Form W2
CONTRACT NO: PWD/HO/B130/2019
PERFORMANCE-BASED CONTRACT FOR THE LONG-TERM MANAGEMENT AND MAINTENANCE OF STATE ROADS [JALANRAYA NEGERI (JRN)] IN SARAWAK - PACKAGE 4 (MIRI DIVISION)
INITIATION OF INSTRUCTED WORK (FORM W2)
|  |  | Superintending Officer's Instruction No.: | [6 empty] | JKR/IW/MR/20/07
| JKR Ref : |  | PWD/HOB/B130/2019/2020(97)(ii) |  |  |  |  | Region :
| Service Provider's Ref : | [6 empty] | Division : |  | MIRI
| Date of Initiation : |  | 2020-09-29 |  |  |  |  | RMU : |  | MIRI
| Attn : |  | Dato' Abg Ariffin Abang Borhan
| Service Provider : |  | Endaya Construction Sdn. Bhd.
| cc : |  | Jurutera Bahagian, JKR Bahagian Miri. (By Fax)
WITH REFERENCE TO THE ABOVE, YOU ARE REQUIRED TO CARRY OUT THE INSTRUCTED WORK AS PER PART A, B, C & D DESCRIBED BELOW:
PART A: LOCATION (to be completed by S.O. or his representative)
Road Code: |  | Q3187 |  |  |  | Chainage Location: |  |  | CH28+970
Road Name: |  | JALAN MIRI MARUDI
PART B: PARTICULARS OF INSTRUCTED WORK (to be completed by S.O. or his representative)
| Title of Instructed Work: |  |  | PROPOSED REHABILATION FOR SLOPE AT CH28+970, Q3178 JALAN MIRI MARUDI PROPOSED REHABILATION FOR SLOPE AT CH28+970, Q3178 JALAN MIRI MARUDIPROPOSED REHABILATION FOR SLOPE AT CH28+970, Q3178 JALAN MIRI
| Date of commencement: |  |  | 2020-12-16 |  |  | (i) Affected due to MCO (i) Affected due to MCO(i) Affected due to MCO(i) Affected due to MCO(i) Affected due to MCO(i) (i) Affected due to MCO(i)(i) Affected due to MCO(i
| Date of completion: |  |  | 2021-04-15
| Instructed Work duration: |  |  | 6 | months
PART C: DETAILS OF WORKS (to be completed by S.O. or his representative)
(Refer to attachment, if appropriate)
i) SP is to liase with Divisional Engineer, or his/her representative.adassdasdadasdad
ii) Works to be implemented as per approval and to be monitored and certified by
Divisional Engineer.
iii) Construction cost shall not exceed the ceiling estimated cost
iv) The Defect Liability Period (DLP) shalle be 12 months from the date issuance of the
Certificate Practical Completion
PART D: CEILING ESTIMATED COST (to be completed by S.O. or his representative)
| RM | 998292.65 |  |  |  |  | Received by: (signature)
| Issued by: (signature) |  | Chong Chi Fam |  |  |  | Dato Abang Ariffin Abang Bohari
| Name & Date: | JKR Bahagian Miri |  |  |  |  | Name & Date: |  | Endaya Construction Sdn. Bhd.
|  | ( S.O. or his representative) | [6 empty] | (Service Provider's Representative)
ENDAYA CONSTRUCTION SDN BHD (049693-V)

## Form WC
FORM WC
JABATAN KERJA RAYA
Miri Division
Jabatan Kerja Raya Miri, Menara 2, Lot 3500
Kompleks Islam Sarawak, Miri, Jalan Pujut
CONTRACT NO: PWD/HO/B130/2019
PEFORMANCE-BASED CONTRACT FOR THE LONG-TERM MANAGEMENT AND MAINTENANCE OF STATE ROADS [JALAN RAYA NEGERI (JRN) IN SARAWAK] - PACKAGE 4 (MIRI DIVISION)
CERTIFICATE OF PRACTICAL COMPLETION
Our Ref. |  | : | PWM/HO/B130/2019(124) |  |  | Date: | 2021-07-22
Your Ref. |  | :
ENDAYA CONSSTRUCTION SDN BHD
Lot 1934,1st-3rd Floor
Marina Square, Phase 2
98000 Miri, Sarawak
Tel: 085-431273
Fax: 085-438647
S.O.'s Instruction No.: |  |  |  | JKR/IW/MR/20/07
Instructed Work Title: |  |  |  | PROPOSED REHABILATION FOR SLOPE AT CH28+970,
Q3178 JALAN MIRI MARUDI
In accordance with Clause 8.9 of the Agreement, it is hereby certified that the Instructed Work achieved Practical Completion on 13/05/2021 And that the Defects Liability Period in respect of the said Instructed Work began on the same day and will end on 13/06/2022 .
'BERSATU BERUSAHA BERBAKTI'
Chong Chi Fam
Superintending Officer
Chong Chi Fam
Jurutera Bahagian

## Form WD
FORM WD
JABATAN KERJA RAYA
Miri Division
Jabatan Kerja Raya Miri, Menara 2, Lot 3500
Kompleks Islam Sarawak, Miri, Jalan Pujut
CONTRACT NO: PWD/HO/B130/2019
PEFORMANCE-BASED CONTRACT FOR THE LONG-TERM MANAGEMENT AND MAINTENANCE OF STATE ROADS [JALAN RAYA NEGERI (JRN) IN SARAWAK] - PACKAGE 4 (MIRI DIVISION)
CERTIFICATE OF DELAY AND EXTENSION OF TIME No…......
Our Ref. |  | : | PWM/HO/B130/2019(128) |  |  |  | Date: |  | 2021-07-25
Your Ref. |  | : | Free Text
ENDAYA CONSSTRUCTION SDN BHD
Lot 1934,1st-3rd Floor
Marina Square, Phase 2
98000 Miri, Sarawak
Tel: 085-431273
Fax: 085-438647
S.O.'s Instruction No.: |  |  |  | JKR/IW/MR/20/07
Instructed Work Title: |  |  |  | PROPOSED REHABILATION FOR SLOPE AT CH28+970,
Q3178 JALAN MIRI MARUDI
In accordance with Clause 8.7 of the Agreement, I hereby grant you extension of time for delay beyond the date of completion or beyond the extended date for completion previously approved, i.e. 15/04/2021, due to the following reasons:-
Reason/reasons | [5 empty] | Clause |  | Period of Delay and Extension of Time
Delay due to Instruction Stop of Work | [5 empty] | 2.1.7.12 |  | 2months
2. The Date for Completion is now therefore extended to 15/06/2021 .
3. Please ensure that yoru performance security and insurances are extended to meet the requirements of the Agreement, if necessary.
'BERSATU BERUSAHA BERBAKTI'
Chong Chi Fam
Superintending Officer
Chong Chi Fam
Jurutera Bahagian

## Form WN
FORM WN
JABATAN KERJA RAYA
Miri Division
Jabatan Kerja Raya Miri, Menara 2, Lot 3500
Kompleks Islam Sarawak, Miri, Jalan Pujut
CONTRACT NO: PWD/HO/B130/2019
PEFORMANCE-BASED CONTRACT FOR THE LONG-TERM MANAGEMENT AND MAINTENANCE OF STATE ROADS [JALAN RAYA NEGERI (JRN) IN SARAWAK] - PACKAGE 4 (MIRI DIVISION)
CERTIFICATE OF NON-COMPLETION
Our Ref. |  | : | PWM/HO/B130/2019(130) |  |  | Date: | 2021-08-22
ENDAYA CONSSTRUCTION SDN BHD
Lot 1934,1st-3rd Floor
Marina Square, Phase 2
98000 Miri, Sarawak
Tel: 085-431273
Fax: 085-438647
S.O.'s Instruction No.: |  |  |  | JKR/IW/MR/20/07
Instructed Work Title: |  |  |  | PROPOSED REHABILATION FOR SLOPE AT CH28+970,
Q3178 JALAN MIRI MARUDI
It is hereby certified that you have failed to complete the Instructed Work mentioned above which was issued to you by the "Date for Completion" stated in S.O.'s Instruction No.: JKR/IW/MR/20/07 dated 15/04/2021, or within any extended time approved under Clause 8.7 of the Agreement, i.e. on 25/07/2021 and in my opinion the said Instructed Works ought to have been completed.
In accordance with Clause 8.11 of the Agreement, you are hereby informed that you are liable to pay or allow to the Government a sum calculated at the rate of 0.0219% per day of the value of this Instructed Work, i.e. RM218.63 per day as Liquidated and Ascertained Damages for the period during which the said Instructed Work shall so remain and have remain incomplete and i shall certify for deduction such damages from any money due or which may become due to you under this Agreement.
'BERSATU BERUSAHA BERBAKTI'
Chong Chi Fam
Superintending Officer
Chong Chi Fam
Jurutera Bahagian

## Form WG
FORM WG
JABATAN KERJA RAYA
Miri Division
Jabatan Kerja Raya Miri, Menara 2, Lot 3500
Kompleks Islam Sarawak, Miri, Jalan Pujut
CONTRACT NO: PWD/HO/B130/2019
PEFORMANCE-BASED CONTRACT FOR THE LONG-TERM MANAGEMENT AND MAINTENANCE OF STATE ROADS [JALAN RAYA NEGERI (JRN) IN SARAWAK] - PACKAGE 4 (MIRI DIVISION)
CERTIFICATE OF COMPLETION OF MAKING GOOD DEFECTS
Our Ref. |  | : | PWM/HO/B130/2019(128) |  |  | Date: | 2021-07-22
Your Ref. |  | :
S.O.'s Instruction No.: |  |  |  | JKR/IW/MR/20/07
Instructed Work Title: |  |  |  | PROPOSED REHABILATION FOR SLOPE AT CH28+970,
Q3178 JALAN MIRI MARUDI
In accordance with Clause 8.10.8 of the Agreement, it is in my opinion that the Defects has been made good on 15/05/2021 .
'BERSATU BERUSAHA BERBAKTI'
Chong Chi Fam
Superintending Officer
Chong Chi Fam
Jurutera Bahagian